## Sheet1
PRIORITY | TASK DESCRIPTION | OWNER | TODO | DOING | DONE | HOURS
1.1 | Documentation PID | Robbert/Dennis |  |  | X
1.2 | Git initalizing | Bart |  |  | X
1.3 | Scrum initalizing | Robbert |  |  | X
1.4 | Hardware ordering | Bart |  |  | X
1.5 | Led Blink Pi 2 | Everyone |  |  | X
1.6 | Install buildroot | Everyone |  |  | X |  | Backlog
SM | [6 empty] | Digital in
2.1 | Kernel module | Everyone |  |  | X
2.2 | Led driver kernel | Everyone |  | X
2.3 | Digital in | Everyone | X
2.4 | PWM | Dennis/Jeroen |  |  | X
2.5 | I2C | Robbert/Bart |  |  | X
SM
3.1 | cross compile module for pi | Everyone | X
3.2 | blink led module for pi | Bart | X
3.3 | porting PWM naar pi2 | Dennis/Robbert | X
3.4 | algoritme besturing | Jeroen | X
3.5 | software architectuur | Dennis | X
3.6
3.7