## Sheet1 (hidden)
PRIORITY | TASK DESCRIPTION | OWNER | TODO | DOING | DONE | HOURS
1.1 | Documentation PID | Robbert/Dennis |  |  | X
1.2 | Git initalizing | Bart |  |  | X
1.3 | Scrum initalizing | Robbert |  |  | X
1.4 | Hardware ordering | Bart |  |  | X
1.5 | Led Blink Pi 2 | Everyone |  |  | X
1.6 | Install buildroot | Everyone |  |  | X |  | Backlog
SM | [6 empty] | Digital in
2.1 | Kernel module | Everyone |  |  | X
2.2 | Led driver kernel | Everyone |  | X
2.3 | Digital in | Everyone | X
2.4 | PWM | Dennis/Jeroen |  |  | X
2.5 | I2C | Robbert/Bart |  |  | X
SM
3.1 | cross compile module for pi | Everyone |  |  | X
3.2 | blink led module for pi | Bart |  |  | X
3.3 | porting PWM naar pi2 | Dennis/Robbert |  | X
3.4 | algoritme besturing | Jeroen |  | X
3.5 | software architectuur | Dennis |  | X
SM
4.1
4.2
4.3

## Sheet2
PRIORITY | TASK DESCRIPTION | OWNER | TODO | DOING | DONE | HOURS | Backlog | Blocking!
1.1 | Documentation PID | Robbert/Dennis |  |  | X
1.2 | Git initalizing | Bart |  |  | X
1.3 | Scrum initalizing | Robbert |  |  | X
1.4 | Hardware ordering | Bart |  |  | X
1.5 | Led Blink Pi 2 | Everyone |  |  | X
1.6 | Install buildroot | Everyone |  |  | X
SM | [6 empty] | Digital IN
2.1 | Kernel module | Everyone |  |  | X
2.2 | Led driver kernel | Everyone |  | X
2.3 | Digital in | Everyone | X
2.4 | PWM | Dennis/Jeroen |  |  | X
2.5 | I2C | Robbert/Bart |  |  | X
SM
3.1 | cross compile module for pi | Everyone |  |  | X
3.2 | blink led module for pi | Bart |  |  | X
3.3 | porting PWM naar pi2 | Dennis/Robbert |  |  | X
3.4 | algoritme besturing | Jeroen |  | X
3.5 | software architectuur | Dennis |  | X
SM
4.1 | Revieuw diagrams | Dennis/Jeroen |  |  | X
4.2 | Interrupts | Bart/Robbert/Dennis |  |  | X
4.3 | Inputs | Robbert |  | X
4.4 | Jeroen model algoritme | Jeroen |  |  | X
4.5 | PWM/ port layout | Robbert |  |  | X
4.6 | Interrupt pwm outputs | Bart/Robbert |  |  | X
4.7 | Soft PWM of timers | Bart/Robbert |  |  | X
SM
5.1 | clock manager | Bart |  |  | X
5.2 | gyro/acc program | Dennis/Robbert |  |  | X
5.3 | gyro/acc performance |  | X
5.4 | motor pwm | Bart |  |  | X
5.5 | algoritme scenario onder bepaalde hoek stabiliteit behouden | Jeroen |  |  | X
5.6 | interfaces: essentiele onderdelen uit algoritme model: snelheid, versnelling, tijd | Robbert | X
SM
6.1 | gyro/acc | r/d |  |  | X
6.2 | algoritme | j | [5 empty] | X
6.3 | bier sensor |  |  |  | X
6.4 | interfaces | r | X
6.5 | pwm module | b |  | X
SM
| solderen MPU6050 (1/2) | Dennis | X
| stabiliseren output (4) | Dennis | X
| normaliseren output (8) | Dennis | X
| stub kernel module (4) | Dennis | X
| pwm module (16) | Bart |  | X
| PID gain var opstart (4) | Jeroen | X | [5 empty] | 2015-07-19 | notes
| PID setp, procvar input (4) | Jeroen | X | [6 empty] | essentieel: gyro/acc, pwm motor, algoritme, hardware
| PID output (8) | Jeroen | X | [6 empty] | doel: balanceren (stilstaan)
| User space aanroepen PID (4) | Jeroen | X | [6 empty] | 3 drivers: pmw, gyro/acc, gpio
tussentijdse beoordeling: aangeven waar op beoordelen